## Gantt Chart
FRA-Pan European Platform
| TASK TITLE | RESOURCES |  | PHASE ONE |  |  |  | PHASE TWO | PHASE THREE
|  | FRA | ECE | MONTH 1 | MONTH 2 | MONTH 3 | MONTH 4 | MONTH 1 | MONTH 1 | MONTH 2
1 | Data migration
1.1 | Analysis of data to migrate | 1 | 1
1.2 | Data migration |  | 1
1.3 | Testing and fine tuning | 0.5 | 1
2 | Statistical Factsheets - PowerBI
2.1 | Definition of the desidered dashboard(s) to visualize | 1 | 1
2.2 | Implementation | ? | ?
3 | Data Tables Visualization within the FRA-Platform
3.1 | Implementation | 1.5
3.2 | Testing and fine tuning |  | 1.5
*2.2 doesn't have a time estimate since the requirements must be discussed